## Sheet1
Person | Work Done | Hours Spent
Ivan Stranski | I created a second DB and created configuration for both DBs.Also I created junit tests for Entities and the User repository. I created user controllers and communication for registering, changing password and deleting user, and created junit tests for said controllers. I also created communication for loging in. I also set up an internal database for junit testing. | ~10
Mihail Spasov | Implented FoodController, which maps 5 server endpoints, namely update, create, find by id, find all, delete by id. Implemented FoodCommunication that sends HTTP requests to the server. Worked on recognizing a user by the http request. I did most of my work in collaboration with Ivan Todorov. | ~10
Ivan Todorov | Implemented FoodService which provides a layer of abstraction on top of the FoodController. Also implemented Food Communication which sends https requests to the Food Service. Worked on integrating the authentication in the food management functionality. Worked on most issues with Mihail. | ~10
Przemyslaw Kowalewski | I implemented three api endpoints regarding user authentication, one used for user creation. (POST /user/create) It validates user input and if it is correct it created the account in the database. The second one (GET /user/all) returns names of all registered users and how many credits the have. | 7
Nathalie van de Werken | Spend time debugging why I got a nullpointerexception somewhere, which I couldn't figure out for a very long time. Then I also spent time figuring out how to test the services (with mocking), which I plan to work on next week. This week I was stuck a lot and in order to have this less in the future I will try to ask. for help sooner. Also in the beginning of the week I worked together with Ivan Todorov to implement adding food to the database, but we were both quite confused on Spring since we both didn't really work with that previously. | 7
Ana Hobai | I worked on what Ivan and Mihail did for the foodManagement. I implemented the findByName method which searches and retrieves the searched food if such food exists in the database in the FoodRepository class. There is also a method in the FoodCommunication class, getFood which will be used to retrieve a list with all existent food in the database (as a menu of foods). In the foodController class I added the deleteFoodPortion for future implementation of the eating food feature which deletes from the database the number of portions a user gives from the specified food. I changed the structure so that we use only the controller for the mapping methods, as I did not see the use of having services. I did the tests for every method in the controller class and added all of my changes to the Tests branch, so that everybody reviews it and approves of my changes. | ~8