## Sheet1
Person | Work done | Hours Spent
Ivan Stranski | Ivan Todorov and I refactored the whole project, due to missunderstandings and pretty much going in the wrong direction. | ~20
Mihail Spasov | Worked on some features that ended up being unneccessary. Also I did some light testing of the FoodController. Overall, this week I was not fully able to contribute to the project due to lack of communication and time. | ~10
Ivan Todorov | Worked with Ivan Stranski on refactoring and rewriting the whole project to start cleanly on a new branch after the team misunderstood/misinterpreted some requirements and our project had a completely wrong structure. | ~20
Przemyslaw Kowalewski | I spent time this week on researching and implementing authentication module with JSON Web Tokens. Users can login using POST /user/login enpoint and if their credentials are correct they are getting the token which they will need to use if they want to be granted access to every secured endpoint. | 11
Nathalie van de Werken | This week I didn't spend that much time on the project as I would have liked, as I was already quite busy with preparing for the midterms. However I did spend some time planning for how to implement the grocerylist feature. Due to the refactoring, the nullPointerIssue that I couldn't figure out for a long time have been solved. | 6
Ana Hobai | Since the architecture was compeltely changed to fit the requirements of the project, I had to redo all the tests for the food-management microservice and also improve them, as well as add some endpoints in the controller. | ~8